## Product_Backlog
Product Backlog
| Project | Burgeen Entrepreneurship and Crowd Funding Platform |  |  | Status | Priority
| Client | JCU Entrepreneurship Club |  |  | To Do | High
| Team Name | Apocalypse |  |  | In Progress | Medium
| Scrum Master | Ming Qian Li |  |  | Done | Low
| Product Owner | Burgeen.com Project Team
Story ID | Title | User Story | Resource | Priority | Status | Comments
1 | Requirement Analysis | Conducting kick-off meeting and subsequent meetings with client to get in depth idea about the project. Thourough analysis of the requirements from implementation perspective. |  | High | Done
2 | Distinguish several functions(Entrepreneur, Information, Sub Websites) | Task need to separate as main functionial systems, crowd funding, information and subwebsite systems Inter-dependency of the drop-down values should be taken care. Ex. If the 'Country' has been selected as 'Malysia' then drop down for 'State' should have list of states from Malysia only. [Use JQuery or Ajax] |  | High | Done
3 | Designing layout and check out with client | According to the prototype which client decided, to finish design and layout. To meet the client again and checkout |  | Medium | Done
4 | User Registration: Sign-Up | Create sign-up page with multiple steps (Basic information, packages available etc). Include 'terms and conditions' checkbox. Distinguish seperately between the mandatory fields and optional fields. |  | High | Done
5 | User Registration: Sign-In | Create sign-in page which will accept UserID and password of the registered user. Include 'Forgot password' functionality. Display ‘Login Failed’ when the user enters incorrect details. Create a ‘Logout’ link for signing out of the account and display on top left (for successful login). |  | High | Done
6 | Payment Portal for crowd funding system | Implement payment gateway using SSL which would accept card details. In case if SSL is difficult to implement, simulate the process. Apply proper validations such as Credit card number should be exactly 16 digits. |  | High | Done
7 | Unit Testing of registration functionality | Write test cases for registration module. Ensure that test cases would cover all validations viz. mandatory field left blank before submitting, password has been selected with optimum strength, valid mail ID is entered. |  | Medium | Done
8 | Plug-in Installation | Install plug-ins for content slider, newsletter, links to social networking sites and site wide search have been installed and configured |  | Medium | Done
9 | Study the required skills | Get acquiented with WordPress, Jquery, Ajax in order to speed up work. Share your knowledge with the team in next Sprint meeting. Share the useful information such as links, docuemnts in 'Knowledge Bank'. |  | High | Done
10 | Setting up the database | Configure the MySQL database and create the required tables. Share the database schema on Google doc. Try to normalize the database as much as possible. Create indexes on relevant columns. |  | High | Done
11 | Displaying results according to search criteria | Establish database connection on click of 'Search' button. Read values from the drop-down boxes and form the SQL query dynamically to fetch the results from the database. Display the retrieved values on the next web page. |  | High | Done
12 | Applying validations on registration form | Apply validations on the various fields from sign-up and sign-in page. Include below validations: a) Mandatory fields should not be left blank before submitting b) Password has been selected with optimum strength c) E-mail ID is entered is valid d) User ID entered is unique |  | High | Done
13 | Creating menu and navigations | Create main menu of the website with tabs home, project, business competition, About US, Contact etc. Also, create the sub-menu and devise and implement the navigation strategy considering whether the link should open in same or new window. |  | High | Done
14 | Adding content to the homepage | Get confirmation from client on various sections and sub-sections of the home page. Collect the contents for all of the finalized sections. Arrange it on the home page appropriately. |  | Medium | Done
15 | Email subscription | Implement a feature for the user to subscribe to various services offered such as newsletter, e-mail notification on new user registration in interested area. |  | High | Done
16 | Functionality to edit [add, modify, delete] user profile | Provide 'Edit Profile' link which will redirect user to new webpage where user can add/modify the registration details such as profile picture, basic details, change in package subscribed etc. |  | Medium | Done
17 | Forget Password' functionality | Currently, only reset password functionality is present. Provide a 'Forgot Password' feature which would ask 'DOB' and some secret question and would send auto generated password to registered e-mail account. |  | Medium | Done
18 | Creating user own website | Creating website for the users based on the multisites funcitons. 1, User can choose the template installed perviously 2, User can design and develop it again 3, User can post contents include pictures, videos and journals |  | Low | Done
19 | Creating the project categories and information categories | Obtain the details from client again, to settle up the categories for projects and business informations |  | High
20 | User own project publish function | User can publish their project, prodcuts or ideas from homepage |  | High
21 | User own website interface | User can have their own dashboard for their website |  | High
22 | Sub-system balance adjustment | the each client project must be tested properly to certain their space, domain-name and the other things can work normally |  | High
23 | Social meida count | the social media count functon must be implement differently in main site and customers sites. |  | Medium
24 | backup functions to database | to backup the data from the whole website, both the main sites and sub-sites |  | High
25 | backup functions to whole website | to backup the files from the whole website, all the contents including pictures and videos. |  | Medium | Done
26 | Commerical module for subsite | the module for the customers who want ot create the shopping mall or the other commerce websites |  | Low | Done
27 | customized silder of sub-sites | the function to enable customers who can create their own silder to demonstrate |  | Medium
29 | Share the like to the social media | the function to enable customers who can share their like from website to social media |  | Medium
30 | Login with social media account | the function to enable user can login the platform using their social media accounts |  | Medium
31 | Arrange the related links | add more related links to platform |  | Low
33 | final result adjustment | including:copyright declaration IP declaration |  | High
34 | prepareation of deliverable process | presentation and demonstartiong to client |  | Medium
Note on A11: A unique ID to refer to this story. Doesn't have to be numeric.
Note on B11: A short title just enough to recall the story.
Note on C11: (from product owner) Description of the user story in common language. Keep it short (one or wo sentences). Usually formatted as: "As a <role> I want to <function> so that <benefit>".
Note on E11: (from product owner) Priority of this story. Use an open scale so you can always move priorities later