## Product_Backlog
Product Backlog
| Project | Burgeen Entrepreneurship and Crowd Funding Platform |  |  | Status | Priority
| Client | JCU Entrepreneurship Club |  |  | To Do | High
| Team Name | Apocalypse |  |  | In Progress | Medium
| Scrum Master | Ming Qian Li |  |  | Done | Low
| Product Owner | Athena Wang
Story ID | Title | User Story | Resource | Priority | Status | Comments
1 | Requirement Analysis | Conducting kick-off meeting and subsequent meetings with client to get in depth idea about the project. Thourough analysis of the requirements from implementation perspective. |  | High | Done
2 | Adding dropdown to the search categories | Need to add the dropdowns for search engine UI with specific categories. All values of the dropdown boxex should be read from database. Inter-dependency of the drop-down values should be taken care. Ex. If the 'Country' has been selected as 'Malysia' then drop down for 'State' should have list of states from Malysia only. [Use JQuery or Ajax] |  | High | Done
3 | Designing layout | Finalize the template as per the discussion with Ms. Ping and team. [Refer the layout sketch shared by Ms. Ping ]. Choosen template should satidfy all requirements mentioned by client. Get go ahead from client on finalized template. |  | Medium | Done
4 | User Registration: Sign-Up | Create sign-up page with multiple steps (Basic information, packages available etc). Include 'terms and conditions' checkbox. Distinguish seperately between the mandatory fields and optional fields. |  | High | Done
5 | User Registration: Sign-In | Create sign-in page which will accept UserID and password of the registered user. Include 'Forgot password' functionality. Display ‘Login Failed’ when the user enters incorrect details. Create a ‘Logout’ link for signing out of the account and display on top left (for successful login). |  |  | Done
6 | Payment Portal | Implement payment gateway using SSL which would accept card details. In case if SSL is difficult to implement, simulate the process. Apply proper validations such as Credit card number should be exactly 16 digits. |  | High | Done
7 | Unit Testing of registration functionality | Write test cases for registration module. Ensure that test cases would cover all validations viz. mandatory field left blank before submitting, password has been selected with optimum strength, valid mail ID is entered. |  | Medium | Done
8 | Plug-in Installation | Install plug-ins for content slider, newsletter, links to social networking sites and site wide search have been installed and configured |  | Medium | Done
9 | Study the required skills | Get acquiented with WordPress, Jquery, Ajax in order to speed up work. Share your knowledge with the team in next Sprint meeting. Share the useful information such as links, docuemnts in 'Knowledge Bank'. |  | High | Done
10 | Setting up the database | Configure the MySQL database and create the required tables. Share the database schema on Google doc. Try to normalize the database as much as possible. Create indexes on relevant columns. |  | High | Done
11 | Displaying results according to search criteria | Establish database connection on click of 'Search' button. Read values from the drop-down boxes and form the SQL query dynamically to fetch the results from the database. Display the retrieved values on the next web page. |  | High | Done
12 | Applying validations on registration form | Apply validations on the various fields from sign-up and sign-in page. Include below validations: a) Mandatory fields should not be left blank before submitting b) Password has been selected with optimum strength c) E-mail ID is entered is valid d) User ID entered is unique |  | High | Done
13 | Creating menu and navigations | Create main menu of the website with tabs home, Investor, Entrepreneur, About US, Contact etc. Also, create the sub-menu and devise and implement the navigation strategy considering whether the link should open in same or new window. |  | High | Done
14 | Adding content to the homepage | Get confirmation from client on various sections and sub-sections of the home page. Collect the contents for all of the finalized sections. Arrange it on the home page appropriately. |  | Medium | Done
15 | Email subscription | Implement a feature for the user to subscribe to various services offered such as newsletter, e-mail notification on new user registration in interested area. |  | High | Done
16 | Functionality to edit [add, modify, delete] user profile | Provide 'Edit Profile' link which will redirect user to new webpage where user can add/modify the registration details such as profile picture, basic details, change in package subscribed etc. |  | Medium | Done
17 | Forget Password' functionality | Currently, only reset password functionality is present. Provide a 'Forgot Password' feature which would ask 'DOB' and some secret question and would send auto generated password to registered e-mail account. |  | Medium | Done
18 | Creating user packages | Creating packages for the users based on the services offered. Three packages which need to be created are: 1) Free: No fee for this account. Only outline of the BP will be available to other users. 2) Pro: S$ 99. Details of the BP woud be made avaialable to first 10 users. User would be required to recharge again to make his/her BP visible to others. 3) Global Pro: S$199 Details of the BP woud be made avaialable to first 40 users. User would be required to recharge again to make his/her BP visible to others. |  | Low | Done
Note on A11: A unique ID to refer to this story. Doesn't have to be numeric.
Note on B11: A short title just enough to recall the story.
Note on C11: (from product owner) Description of the user story in common language. Keep it short (one or wo sentences). Usually formatted as: "As a <role> I want to <function> so that <benefit>".
Note on E11: (from product owner) Priority of this story. Use an open scale so you can always move priorities later