## Sprint-Backlog
Sprint Cycle: 3 Weeks
Sprint Dates: April 1 - April 18,2014
Sprint Goal
To finish all the project
| Working Hours |  |  |  |  | Working Hrs/Week |  |  |  | Priority
| Number of Weeks | 3 | [7 empty] | Must
| Total Resources | 3 | [7 empty] | Should
[6 empty] | 10 |  |  |  | Could
[6 empty] | 10 |  |  |  | Wont
10
|  |  |  | Total man hours in Sprint |  | 97.5
|  |  |  | Total man hours/day |  | 4.6429
Task Burn Down
[7 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3
| Task ID | Story ID | Priority | Description | Resource | Initial estimate | 2013-11-01 | 2013-11-02 | 2013-11-03 | 2013-11-04 | 2013-11-05 | 2013-11-06 | 2013-11-07 | 2013-11-08 | 2013-11-09 | 2013-11-10 | 2013-11-11 | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-16 | 2013-11-17 | 2013-11-18 | 2013-11-19 | 2013-11-20 | 2013-11-21
| 1 |  | Must | Meeting the client regarding requirements | Team | 7.5 | 6 | 6 | 6 | 6 | 4.5 | 4.5 | 4.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 2 |  | Must | Discussion about requirements, within the team members | Team | 12 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 3 |  | Should | Preparation of product and sprint backlog | Team | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 4 |  | Must | Testing sign-in and sign-up functionality for user registration | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 5 |  | Must | Developing the initial user interface for search engine | Team | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| 6 |  | Must | Display all the results according to search criteria | Team | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 16 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
| 7 |  | Must |  | Team | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 |  | Should |  | Team | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 20 | 18 | 18 | 17 | 16 | 15 | 14 | 14 | 14 | 13 | 10 | 7 | 4 | 0 | 0
| 9 |  | Should |  | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 |  | Should |  | Team | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Total | 10 |  |  |  |  | 97.5
|  |  |  | Remaining Hours ( Actual) |  |  | 93 | 93 | 93 | 93 | 88.5 | 88.5 | 82.5 | 62 | 59 | 55 | 44 | 42 | 40 | 33 | 32 | 26 | 17 | 13 | 3 | 0 | 0
|  |  |  | Tasks Remaining |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 8 | 7 | 4 | 3 | 3 | 0 | 0
Issues
Team Member
| MingQian Li | 12781351
| Tyrza, Adelia Winata | 12847737
| YiRan,Pan | 12902622
Note on B24: A unique Task Id
Note on F24: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on G24: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.